## Project Planner
UI implementation for Victoria state accident dataset
Select a period to highlight at right. A legend describing the charting follows. |  |  |  |  | Period Highlight: | 26 |  |  | Plan Duration | [5 empty] | Actual Start |  |  |  |  | % Complete |  |  |  |  | Actual (beyond plan) | [7 empty] | % Complete (beyond plan)
ACTIVITY | PLAN START | PLAN DURATION | ACTUAL START | ACTUAL DURATION | PERCENT COMPLETE | PERIODS
[6 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 54 | 55 | 56 | 57 | 58 | 59 | 60
Level 1 Planning the Project | 1 | 9 | 1 | 9 | 100%
1.1 Meeting Clients | 1 | 2 | 1 | 2 | 100%
1.1.1 Defining time requirements | 1 | 1 | 1 | 1 | 100%
1.1.2 Defining UI requirements | 2 | 1 | 2 | 1 | 100%
1.2 Defining team roles | 3 | 1 | 3 | 1 | 100%
1.3 Team requirements | 4 | 1 | 4 | 1 | 100%
1.4 Definig the project | 5 | 2 | 5 | 2 | 100%
1.4.1 Provide project background | 5 | 1 | 5 | 1 | 100%
1.4.2 Provide scope for the project | 6 | 1 | 6 | 1 | 100%
1.5 Scheduling the work | 7 | 3 | 7 | 3 | 100%
1.5.1 Create WBS | 7 | 1 | 7 | 1 | 100%
1.5.2 Creating activity definition & estimation | 8 | 1 | 8 | 1 | 100%
1.5.3 Creating Gantt chart for the project | 9 | 1 | 9 | 1 | 100%
Level 2 Defining design requirements of the project | 10 | 16 | 10 | 16 | 100%
2.1 Defining GUI design requirements | 10 | 6 | 10 | 6 | 100%
2.1.1 Creating drop down for time periods | 10 | 2 | 10 | 2 | 100%
2.1.2 Display data for the selected time period | 11 | 1 | 11 | 1 | 100%
2.1.3 Display the accidents through keywords | 12 | 1 | 12 | 1 | 100%
2.1.4 Dislpay the number of accidents | 13 | 2 | 13 | 2 | 100%
2.1.5 Display the data visualisation of alcohol | 15 | 1 | 15 | 1 | 100%
2.2 Drop down table requirements | 16 | 2 | 16 | 2 | 100%
2.2.1 Butons for time period | 16 | 1 | 16 | 1 | 100%
2.2.2 display time period data | 16 | 1 | 16 | 1 | 100%
2.2.3 Accidents per speed zone | 16 | 1 | 16 | 1 | 100%
2.2.4 Accidents per hour (average) | 17 | 1 | 17 | 1 | 100%
2.2.5 Search by keywords | 17 | 1 | 17 | 1 | 100%
2.2.6 Alcohol impacts | 17 | 1 | 17 | 1 | 100%
2.3 Defining software design requirements | 18 | 8 | 18 | 8 | 100%
2.3.1 Python | 18 | 5 | 18 | 5 | 100%
2.3.1 Streamlit | 23 | 3 | 23 | 3 | 100%
Level 3 Code creation and Streamlit UI | 26 | 26 | 26 | 26 | 100%
3.1 Creating Python Code and UI | 26 | 20 | 26 | 20 | 100%
3.2 Software testing | 46 | 4 | 46 | 4 | 100%
3.2 Program support | 50 | 2 | 50 | 2 | 100%